STRENGTHENING COMMUNITY POLICING IN ALBANIA

FORCIMI I POLICIMIT NË KOMUNITET NË SHQIPËRI

Implemented by:

BI-ANNUAL PROGRESS REPORT

(December 2019)

| Project title | Strengthening Community Policing in Albania, 2nd phase, Program implementation 2017-2020 |
| --- | --- |
| Project No. | UF2014/52825/TIRA |
| Country | Albania |
| Funding Agency | Sida |
| Implemented by | FCG Swedish Development AB |
| Address | Dalagatan 7, 111 23 Stockholm, Sweden Web: www.fcgsweden.se ++46 8 406 76 20 |
| Contact person | Mr. Pontus Förberg, Project Director FCG Cell: +46 70 214 21 81, Office: +46 8 406 76 20 pontus.forberg@fcgsweden.se |
| Date of report | 31 January 2020 |
| Reporting period | 1st July 2019 – 31 December 2019 |
| Chair of Project Steering Committee | General Director of Albanian State Police |
| FCG Project Team Members | Mr. Ansi Shundi, Team Leader Mr. Ulrich Dugas, International Police Advisor Mr. Enri Hide, Long Term Advisor Mr. Frank Harder, M&E Expert Mrs. Eldisa Zhebo, Long Term Advisor Mrs. Miranda Fishka, GS Manager, DV Expert Mr. Arian Braha, Program Coordinator Mrs. Jolanda Gugaj, Program Officer |
| SCPA Contacts | Address: Blv “Zhan D’Arc”, Nd. 61, H.5, K. 5, Ap. 6, Tirana, Albania. Tel + 355 44 511 340 Mail: info@cp-project.al Web: www.cp-project.al |

Table of Contents

ACRONYMS AND ABBREVIATION	4

1.	Executive Summary	5

2.	Progress achieved based on Program Pillars	6

2.1	Pillar I – Local Police Directorate Community Policing Support	6

2.2	Pillar II – Strategic Management Support	12

2.3	Pillar III – Domestic Violence Support	17

2.4	Horizontal Activity - Grants Scheme	21

3.	Budget expenses	23

4.	Focus for the next phase	23

Annex I – Updated Logical Framework	24

Annex 2 Risk Matrix	30

Annex 3 - Participants/beneficiaries in SCPA activities	33

# ACRONYMS AND ABBREVIATION

ASP		-	Albanian State Police

CP		-	Community Policing

CPO		-	Community Policing Officer

CSS		-	Community Safety and Security

DV		-	Domestic Violence

DVS		-	Domestic Violence Support

ESS		-	European Social Survey

EU		-	European Union

EUR		-	Euros

GD		-	General Director [of the ASP]

GoA		-	Government of Albania

GS		-	Grants Scheme

HQ		-	Headquarters

ICITAP		-	International Criminal Investigative Training Assistance Program

IOM		-	International Organization for Migration

IPA		-	International Police Advisor

ISSAT		-	International Security Sector Advisory Team

SC		-	Steering Committee

JWG		-	Joint Working Group

LCPS			Local Council on Public Safety

LPD		-	Local Police Directorate

M&E		-	Monitoring and Evaluation

MoI		-	Ministry of Interior

MoJ		-	Ministry of Justice

NGO		-	Non-Governmental Organization

NSDI		-	National Strategy for Development and Integration

OSCE		-	Organization for Security and Cooperation in Europe

PAMECA	-	Police Assistance Mission of the European Community to Albania

PMS		-	Performance Management System

PMT		-	Project Management Team

SACP		-	Swedish Support to the MoI / ASP on Community Policing

SAPEMR	-	Sector of Strategic Analysis, Planning, Evaluation, Monitoring and Reporting

SCPA		-	Strengthening Community Policing in Albania

Sida		-	Swedish International Development Cooperation Agency

SMS		-	Strategic Management Support

SSR		-	Security Sector Reform

SOP			Standard Operating Procedure

TLPD		-	Target Local Police Directorate

TWGs		-	Technical Working Groups

UNDP 		-	United Nations Development Program

UNHCR		-	United Nations High Commission for Refugee

UNICEF		-	United Nations Children’s Fund

USAID		-	United States Agency for International Development

# Executive Summary

The SCPA project entered the last year of its implementation in January 2020. The last semester was important in fostering the achievements made in close and fruitful cooperation with the ASP and other stakeholders. Although the activities in general were smoothly implemented and as planned by the program work plan, some activities were affected by the extraordinary situation caused due to the November earthquake. However, the deviations from the program were very limited and will be recovered during 2020.

The project’s experts and the lecturers from the Academy of Security continued to deliver the training for the CPOs in LPDs Diber, Fier, Korça and 3 groups from Tirana LPD. During this reporting period 230 CPOs were trained. Overall 555 CPOs have been trained so far. The remaining 80 CPOs will be trained in February 2020 (the training was postponed due to the earthquake). At the conclusion of the training, the lecturers will identify what will be the elements from the training to be included in the main curricula of the Safety Academy.

In response to the approval, in principle of the recommendations related to the streamline of the CPOs activity in the TLPDs, the TWG elaborated a new job description for CPOs, general patrol and command and control officers. After formal adoption of new work practices, their implementation will start piloting in Elbasan LPD. Additionally, the CPOs will be supported and assisted to make the “police zone” functional.  An assessment of the current working procedures for CPOs is completed and the need for an SOP identified. If approved, the work will start immediately in 2020.

To combine the support for the working procedures with enhancement of work premises especially in rural areas, an inventory of the current status with regard to equipment and premises in LPD Elbasan has been done and an investment plan drafted. The project will support the CPOs with laptops and refurbishments for their offices in rural areas, located in the premises of the administrative units. The project also supported the development and publication of a customized leaflet for the CPOs.

The project continued with funding the investments to improve the police infrastructure. The reception hall of Tropoja Commissariat and the old detention premises were reconstructed for a total amount of 27.500 euro. The project financed 22.500 euro, while the business community of Tropoja contributed with the remaining amount. Based on the models seen in Croatia and Germany, the project supported the establishment of a prevention room in Kukes LPD. This will be used as a space to meet and share with the public different presentations and awareness raising events. Posters on bullying, drug abuse, road traffic rules, community policing and domestic violence were printed and will be posted in this room and in other commissariats.

With a view to enhance the exchange of information and collaboration among local partners, the project contributed, through grantees, to the establishment of three Local Councils of Public Safety in Peqin, Vlora and Selenica municipalities. Preparations have started in the municipalities of Korça and Lezha, where first meetings were organized. The target for the first semester of 2020 is the establishment of the LCPS in Kukes municipality.

A SOP for the Sector of Strategic Analysis, Planning, Evaluation, Monitoring and Reporting (SAPEMR) was approved by the ASP General Director and enacted on 21 November 2019. This SOP is based on the draft elaborated by the SCPA program experts, reflecting the content of the training delivered to the staff of the Sector of SAPEMR. It explains in detail the responsibilities, proceedings, the flow of information required by the new sector and the overall internal communication and cooperation flow between all sectors, sections and commissariats within every LPD.

As a follow up of the workshop with the LPDs Directors organized in July, a number of awareness workshops took place in December 2019 (Shkoder, Korca, Vlora, Fier, Elbasan, Kukes, Diber, Lezha), with the participation of the representative of the ASP HQ. The meetings were attended by Head or Deputy Head of these LPDs, staff of the Sector for SAPEMR, and heads of other sectors in key commissariats. The approved SOP for the Sector for Strategic Analysis was introduced to the participants, along with discussions and information sharing on different progress reports, analysis, evaluation and recommendation regarding the LPD annual strategy.

Coaching and support continued in the two pilot LPDs of Elbasan and Kukes, particularly given that both Heads of Sectors trained previously by the SCPA have been transferred to other positions in the ASP.

In December the project disseminated the results of the last Local Safety Measurement System in Elbasan and Kukes regions. The survey is conducted in 2600 households in these two regions. The results are being discussed with the two LPDs and will be shared with all the members of the LCPS in the concerned municipalities, to form the basis for their discussions and decision making.

The project continued to support the awareness raising campaigns organized by the ASP in schools all over Albania. In October a workshop with all the CPOs Youth Educators and other police officers appointed to run the campaigns in different cities was organized. 60 police officers participated in this event. They shared the experience of the previous school year and discussed the challenges for the new season. In the period September- December 2019, 225 awareness activities took place in a total of 169 schools. Facebook continues to be a powerful tool and most of the participants are very active posting and sharing information. These activities are very much appreciated by the local communities and local authorities. Recently, the Municipality of Lezha awarded the two CPOs from Lezha Commissariat with Certificates of Appreciation for the work performed in schools.

To further extend the outreach to the youth generation, the SCPA project will train the security officers in secondary schools to enable them deliver the same awareness raising campaigns in their schools. The plan is to deliver training to around 180 security officers and social workers all over Albania. This significant number of police officers and security officers (240 in total) will be engaged to deliver different safety related messages, especially during the campaign “2020 the year of traffic safety” promoted by the ASP and the MoI. The project will support the police officers with laptops and projectors, as well as with other logistical/promotional materials.

The project continued to support the activities of the Multidisciplinary Technical Teams on Domestic Violence in three municipalities (Gramsh, Belsh and Kukes), while support the revitalization of the mechanism in Peqin and Librazhd. These activities were combined with the campaign of 16 days against violence against women, implemented in 6 municipalities in November – December.

A training for the police officers in Kukes LPD on the amendments of the law against domestic violence and the new form of risk assessment was also delivered. 42 police officers where trained in this LPD, while Elbasan LPD officers will be trained in 2020.

In Elbasan LPD the premises for the Interview Unit for Minors and Victims of Domestic Violence were renovated and refurbished. This is the first set of equipment of this type installed in Albania, enforcing the provisions of the Code for Criminal Justice for Children, allowing recording of the victim’s interview in the presence of defence lawyers and prosecutors. Special software is installed to manage the information. The program provided 19.000 euro for the equipment and 5.500 euro for reconstruction and refurbishment of the premises.

In parallel to the activities carried out in the frame of Round 3 of the Grant Scheme, the project issued the 4th call for applications, covering Tirana, Kukes and Berat regions. 16 out of 17 grants of Round 2 completed the activities during the reporting period. All grants of Round 3 are being implemented following the timelines and plan of activities. For the 4th Round, we have received 26 applications in total. The selection of the winners will be completed in February 2020 and NGOs will start implementation in March 2020.

# Progress achieved based on Program Pillars

The activities of the Program were implemented in line with the Inception Report and the Action Plan approved by the JWG and the SC. Overall, the program’s activities are well on track and in some cases activities foreseen for a later stage already started implementation. Divided in pillars, the main activities implemented are as follows:

## Pillar I – Local Police Directorate Community Policing Support

Pillar I constitutes the core of the project and many of the activities implemented during the reporting period are part of this pillar. The activities under this pillar are grouped in three sub-components:

1.1. Support the ASP to enhance the efficiency of the CP structure

Based on the results achieved during the previous phase, the activities under this subcomponent focused on support of the TLPDs with coaching delivered to CPOs of some commissariats and to their supervisors. The coaching process was accompanied by an evaluation process of the work and efficiency of CPOs and their supervisors. A special report was drafted and discussed with the Joint Working Group on recommendations to enhance the situation of CPOs and their daily work and to vitalize CP with more sustainability. During the next semester the activities will focus on implementation of the recommendations from the report and efficient implementation of the “police zone” concept in TLPD Elbasan.

Activity 1.1.f. Coach, monitor and assess the CPO work and Activity 1.1.d. Check and revise SPOs for CPOs

The assessment report on CPOs tasks and functions included a set of recommendations to streamline the function of CPOs, which were sent to the ASP HQ. The Joint Working Group proposed to establish a Technical Working Group (TWG) including ASP HQ staff, Tirana LPD and the program experts in order to further elaborate the implications of the recommendations and prepare the path for their implementation. Initially, the TWG was tasked with the development of a new CPO job description to reduce the task load of the CPOs and shift the responsibility for urgent police operations to the General Patrol Police as it was agreed with the ASP Department of Public Security. The project experts drafted a revised job description, which was then finalized during discussions with the TWG. During TWG meetings, it became evident that the amended CPO job description affected the tasks of other structures at the LPD level, in particular those of Patrol Police and Command and Control Sector. Supported by the project the TWG submitted a Progress Report to the ASP Department of Public Security. The report refers amongst others:

- to the new CPO job description which is still awaiting approval

- the development of a SOP for CPOs that doesn’t exist till now

- the revision of job descriptions and SOPs of the Patrol Police and the staff of the Command and Control Sector and

- the implementation of necessary changes in the TLPD Elbasan for a pilot phase.

The piloting activities were suspended following the unfortunate events of November 2019 in Albania and will continue during 2020. They will start with a kick off workshop in Elbasan LPD where high level officials from ASP Headquarters will be present. The whole piloting phase of the recommended activities will be closely monitored by the program experts and the representatives of the TWG. In order to facilitate the process, the program drafted the respective milestones for the work. They will be discussed with the Working Group and thereafter submitted to the ASP HQ.

Furthermore, during discussions when training and coaching CPOs, it was evident that they are burdened with tasks which are not included in their job description. Hence the project started a baseline study and conducted some interviews with CPO supervisors of the Commissariats Elbasan, Peqin, Kukes and the Police Station Belsh, as well as in Kukes LPD. The aim was to check the accuracy of the daily CPO activities, reports and statistics compiled by LPDs and CPOs and how they are used to plan the daily activities of the staff and the workforce. The interviews covered the tasks completed in the first 9 months of 2019. From the findings, it is clear the statistics are not very useful for planning purposes. The way how the statistical data are recorded and interpreted partly varies between the LPDs and between the commissariats within the same LPD. The main reason for the differences in registering of statistical data is the lack of a national regulation or guideline for reporting these data. In conclusion, by interviewing CPO supervisors and through intensive discussions with ca. 500 trained CPOs the project has made the heavy work load of CPOs clearly evident.

Activity 1.1.g. Provide the CPOs with material support and communication means

In order to assess the needs of material and communication means of the CPOs in Elbasan TLPD, the program developed a questionnaire. The aim is to provide the CPOs in rural areas, who have an office, with adequate furniture, Personal Computer (PC) and templates for the reports or applications that they use. The CPOs should have access to the Case Management System (CMS) and to the Total Information Management System (TIMS) to make checks of individuals. The PCs can also be used to share information via special forms SK 1 and SK 2. In the future CPOs should compile intelligence police information in their office and send SK 1 and SK 2 as email attachment to the commissariat to be saved into MEMEX. Currently the CPOs have to go to the commissariat within 24 hours in person to submit these forms, which is very time and resource consuming. It is much more time-efficient to deal with all these issues from the zone offices. Having all these facilities in zone office, the CPOs would be able to carry out their main task, which is to be present in the zone and serve public there.

In order for the CPOs to reach as many persons as possible, the program developed a CPO leaflet.  The main purpose is to inform the citizens about “his/her” CPO, the duties and how to reach him/her. The below leaflet were distributed to all CPOs in all commissariats. They found this means of communication very innovative and useful.

The program also supported the establishment of an information and prevention room in the TLPD Kukes. These new premises are equipped with all the necessary tools for public meetings and presentations. The model has drawn inspiration from the prevention rooms visited in Croatia and Germany during the study visits. It will be inaugurated in January 2020.

A set of posters on bullying, drug abuse, road traffic rules and community policing is prepared for this prevention room and for other public premises in TLPDs and commissariats.

Activity 1.1.i. Support to enhance the Reception Hall infrastructure in TLPDs and services provided by all RHs.

After Librazhd Commissariat, the efforts to enhance the reception halls were focused on Tropoja Commissariat in Kukes LPD. The RH premises were built several years ago and the conditions were poor, as humidity and water leakages from the roof damaged the walls.

With partial support from the local business community, reconstruction of the RH and old detention premises in the commissariat were undertaken. The project covered 22.500 euro, and the business community contributed with additional 5.000 euro. The works were completed in December and inauguration of the premises will take place in January 2020.

Before:

After:

Following the decision from the Albanian Government to shift all applications for services to the online platform e-Albania, the project has temporarily suspended the activities for the development of the RHs’ software. The situation is clear now and the works will resume immediately for the elaboration of this software.

1.2. Strengthening local partnerships

Activity 1.2.j. Initiate and support the establishment and working of regional/local safety and security councils in the municipalities included in the two TLPDs. In the municipalities where they exist, support proper functioning and discussion of common concerns related to security and safety in the neighbourhoods.

During the reporting period, the project contributed, through grantees, to the establishment of three  Local Councils of Public Safety in Peqin, Vlora and Selenica municipalities. Preparations have started in the municipalities of Korca and Lezha and representatives of the different institutions and civil society have met in this period. The formal establishment of the LCPS is expected during the first semester of 2020. Through different grant contracts the project will support the functioning of these councils in the upcoming period.

1.3. Capacity building to transform ASP into a modern citizen and service oriented organization

Activity 1.3.m.3. Deliver training in cooperation with the Academy for CPOs of all LPDs

Just as in the previous period the training of CPOs was one of the main tasks. The cooperation with the lecturers of the Academy for Public Security successfully continued. Due to ongoing developments in the Police, new training exercises were designed and coordinated with the lecturers of the Academy. In the first week of October the training was delivered to 42 CPOs of the LPD Diber. Thereafter the experts of the program and the lecturers of the Academy conducted the training for 81 CPOs of the LPD Fier and 48 CPOs of the LPD Korce. Due to the earthquake and the emergency situation in December the training was delivered only for 59 CPOs of the LPD Tirana (3 groups). The remaining 80 CPOs will be trained in February 2020.

In this reporting period 230 CPOs were trained. Overall 555 CPOs have been trained so far.

A huge part of the training was dedicated to the role of CPOs in the ASP and society, the exchange of experiences, prevention activities and the cooperation with other organizations as well as with citizens. The participants appreciated the content of the training and the methodology used. They evaluated the training achievement with the highest scores.

## Pillar II – Strategic Management Support

The activities under this pillar are divided in three subcomponents:

2.1. Strategic planning and performance evaluation

The activities under this sub-component are focused on improving the system of strategic planning and performance evaluation within the ASP and MoI by increasing capacities to collect, analyze and use data to inform management, identify and communicate better results achieved by the ASP. The activities of the program are centered around the newly created Sector of Strategic Analysis, Planning, Monitoring and Evaluation in all LPDs.

Activity 2.1.d. The two TLPDs will be supported during implementation of their local strategies based on the Community Policing Document, elaboration of periodic progress reports and identification of bottlenecks and recommendations to improve the situation.

A workshop for all LPD Directors was organized and took place in July 2019, with the aim to discuss the functions and the role of the newly created Sector for Strategic Analysis, Planning, Evaluation, Monitoring and Reporting. The participants in the workshop discussed their expectations and how they see the role of the sector against the tasks they have to do. Overall the sector is appraised as very valuable for the LPD directors and they consider it as an added value to their managing work in the LPD. A summarized picture of the training, which all analysts attended, was presented to the directors. By examples it was explained what they can expect from the new sector and its staff and what are the benefit this new Sector yields in the future.

A SOP for the Sector of Strategic Analysis, Planning, Evaluation, Monitoring and Reporting (SAPEMR) was approved by the ASP General Director and enacted on 21 November 2019. This SOP is based on the draft elaborated by the SCPA program experts, reflecting the whole content of the training delivered to the staff of the Sector of SAPEMR. It explains in detail the responsibilities, proceedings, the flow of information required by the new sector and the overall communication and cooperation flow between all sectors, sections and commissariats within every LPD.  Initially the SOP included solely the forms of weekly / monthly reports, but the SCPA experts deemed as relevant for the SOP to contain a yearly reporting format too, which is in line with all guidelines provided in the SOP.  Therefore, as agreed with the ASP HQ,  the reporting forms were revised and partially changed to reflect the reporting needs for biannual and annual reporting processes of LPDs. These changes have been approved by the Sector of Strategic Studies in the HQ.

As part of the support and coaching process for the Sector of SAPEMR regarding the new SOP, a number of awareness workshops took place in December 2019, (Shkoder, Korca, Vlora, Fier, Elbasan, Kukes, Diber, Lezha), with the participation of the representative of the ASP HQ (Sector of Strategic Planning). The meetings were attended by Head or Deputy Head of these LPDs, staff of the Sector for SAPEMR, and heads of other sectors in key commissariats. The following topics were discussed:

-	Introduction of the newly approved SOP for the Sector for Strategic Analysis

-	The bi-annual and annual reporting process in terms of process, communication, analysis, evaluation and recommendation regarding the annual strategy (both main and local strategy).

-	How the recommendations of the annual report will feed the preparation of the upcoming annual LPD strategy and the respective actions and guidelines for such processes based on ASP HQs (to be ready on 15 January 2020).

A guideline for the development of strategies and action plans has already been compiled by the program.

Coaching and support continued in the two pilot LPDs of Elbasan and Kukes, particularly given that both Heads of Sectors trained previously by the SCPA have been transferred to other positions in the ASP.

The new Sector for Strategic Analysis in each LPD still lacks human resources in terms of staff and capacities (due to the frequent reshuffling of staff). Additionally, in many LPDs the sector lacks proper equipment, like computers and printers. The ASP Public Order Strategy 2013-2020 ends in 2020 and quite soon in second quarter of 2020 the ASP HQs will establish a task force to draft the new strategy. This will be a good opportunity for SCPA to continue its support to strategic planning process for LPDs.

Activity 2.1.e. Increasing capacities to systematically use external monitoring mechanisms to evaluate performance

Based on the Joint Working Group decision, in autumn 2019 the second survey of the Local Safety Measurement System (LSMS) in two pilot LPDs Elbasan and Kukes was carried out. The results were available in December and were distributed to the police counterparts. The aim of the LSMS is to measure the level of safety as it is perceived by the community, including real crime levels, disorder problems, traffic security as well as the level of satisfaction with the police work in 8 defined Commissariats in the 2 TLPDs. Local Safety Measurement System provides information on 5 important issues for safety and order in community.

- Problems and Disorder in the community

- Crime Exposure of residents,

- Residents’ concerns on safety in their community and living areas

- Concrete feelings of fear and insecurity (concerns on security issues)

- Satisfaction with police work in the community

The survey was conducted in October – November 2019 in 13 designated areas. The “zones” coincide with the “Police zone” in each commissariat having  in average 10.000 – 20.000 inhabitants. The survey is conducted in 2600 households in Elbasan and Kukës Districts where 200 interviews are completed  in each area / zone.

In 2019, there is generally a noticeable improvement in some problematic issues compared to 2018, such as:

- The problem of environmental pollution - in 2019 has decreased by about 1.2 % compared to 2018

- Infringement of private or public property - in 2019 has decreased by about 8.5% compared to 2018

- Distribution and use of drugs - in 2019 has decreased by about 4.3% compared to 2018

- Breach of public order and street fights - in 2019 has decreased by about 5.8% compared to 2018

- Harassment of women and girls in public places - in 2019 has decreased by about 5.4% compared to 2018.

- Noises from the bars or other entertainment places - in 2019 has decreased by about 14.3% compared to 2018.

- Youth gangs’ activity - in 2019 has decreased by about 4.5% compared to 2018.

- Violations of road traffic rules - in 2019 has decreased by about 7.5% compared to 2018.

The LSMS 2019 data show the following issue to have increased compared with the LSMS 2018 data:

- The car movement speed beyond the allowed speed limit (0.4%).

Part of the report (tables with the results) are attached as Annex 4 to this report.

During January-February 2020 the project will start a process of discussions of LSMS results in LCPS in Elbasan and Kukes, trying to involve all local stakeholders in safety issues in the community.

2.2.3. Support communication processes and capacity building

Communication with the external stakeholders as well as within the organization is vital for the Police to increase the support and cooperation with them. In this regard the program supported the TLPDs and the HQ to carry out several activities.

Activity 2.3.h Support the ASP to implement the Integrated Communication Strategy and Activity 2.3.i. Support implementation of national awareness campaign

Being aware that youth interactions present a unique set of challenges and opportunities for the police, the SCPA program has stepped up efforts to consolidate the pool of around 60 Youth Educators in knowledge and expertise on the awareness topics as well as in communication skills.

In order to achieve this, during October 2019, the program organized an interactive workshop with all youth educators from 12 LPDS. This already well-established practice had a dual purpose: on the one hand, it was conceived as a continuation of capacity building on awareness-raising topics involving discussions on the progress and encountered difficulties; on the other hand, the workshop focused on the theoretical and practical handling of techniques for effective communication with different audiences, as well as on professional development in the process of conveying the messages and knowledge needed in this regard.

More specifically, the content of the workshop was developed in such a way as to enable the further development of the capacities built earlier and to gather valuable information on:

- Best methods to implement their working plan

- Increasing knowledge on submitted awareness -theoretical materials prepared by the program

- Their professional development and further needs.

With the aim of fostering sustainable, long-term, pool of youth educators the program experts placed considerable efforts to have the previously trained Educators share experience with new CPOs, and to harmonize the group.

SCPA intends to continue this practice and organize periodical workshops prior to starting a new awareness topic for reasons of sustainability and adjusting the methods and practice to circumstances on the ground.

The evidence from ASP HQ CP Sector and the feedback collected by the program on weekly basis, demonstrated that this group of activities yielded positive outcomes across the whole country. Many CPOs-youth educators reported growing demands from numerous school principals to develop more awareness lectures in their schools. Unfortunately, these proven useful programs are not available to all students who need and want the opportunity.

For this reason, SCPA discussed and started making necessary preparations to extend delivering the awareness topics either in other grades in secondary schools or in high schools, by making use of School Security Officers. A number of meetings were organized involving ASP HQ public safety officials and Ministry of Education and Science directors, responsible for secondary education. The meetings aimed at discussing the feasibility and logistical preparation of training around 150 school security officers. In principle, all the three above institutions have agreed to start the training program in the nearest future. The SCPA program has made all preparations and is ready to conduct a training cycle with them, in cooperation with the Security Academy, as soon as the final agreement has been adopted by the relevant authorities.

Meanwhile, SCPA noted that some conclusions and suggestions should be paid heed to, in order to run the whole process smoothly.

- -Personnel assigned to deliver awareness topics should be consistent.

Considering the composition of participants in the 4 trainings conducted so far, we note that the turnover was high. 15 trainees are no longer involved with delivering the awareness topics in schools from the initial group, while 10 of the trainees are performing 2 functions in parallel (patrol service or CPO) and delivering lectures at the same time. Some trainees informed that it was impossible to accomplish the topics in schools when they worked as night patrols. It is recommended that Tirana LPD should definitely assign CPOs as dedicated youth educators for each commissariat, as this is the region with the highest number of schools in its territory.

- New staff need more in-depth training.

29 CPOs have completed all the training sessions so far. The rest are newly appointed for this task and do not necessarily have all communication and presentation skill. In order for the group of educators to have the same level of skills, the SCPA program suggests that newly appointed educators (30 people) be trained for 2 -3 days additional session.

- The need to integrate web constable with the tasks of the youth educator

During the last training the topic of the web constable and the need to integrate this practice with the awareness program were also touched upon. Many of the trainees stated that current spokespersons assigned at the LPDs find it virtually impossible to deliver this practice on time and in quality. Participants expressed interest in reactivating this practice.

- There is a need for further cooperation enhancing with the local education directorates.

Special emphasis was also placed on extending greater cooperation with the Local Education Directorates (DAVs) and the respective school directorates. The experiences of the CPOs of Durres, Tirana, Elbasan, Kukes as well as Saranda and Vlora from working with school coordinators were discussed and considered as a good practice to be implemented by others.

The participants highly valued the awareness modules leaflets and brochures produced by the SCPA program.

National awareness campaigns:

From July to December 2019, the youth educators conducted regular awareness meetings on topics such as abuse of drugs, alcohol, and tobacco as well as road safety in all LPDs. The program, in cooperation with the CP sections at LPD level as well as in coordination with ASP HQ, monitored, advised and coached where necessary the whole activity of the youth educators in almost 12 LPDs. In accordance with the work plan 23 CPOs, or 38 % of the total, started delivering the awareness topic on road safety. The TLPDs of Kukes and Elbasan, but also some commissariats of Tirana, Durres, Lezha, and Shkodra LPDs,  were well on track with the work plan.

During November 2019, the youth educators were also involved in the national awareness campaign “16 days activism against gender based violence”. The Program offered prompt assistance and material support to the TLPDs of Elbasan and Kukes and also to some other LPDs where found necessary.

In general, youth educators have committed an estimable job during this reporting period in implementing awareness programs and enhancing collaboration with youngsters. They have made strides ahead to enhance cooperation and trust with the community.

Also, the program expert provided systematic assistance to a number of youth educators for improving the quality of national awareness campaigns to enable the ASP to get closer to the public and increase cooperation.

SCPA has, on a daily basis, monitored the online forum to keep both ASP and the program informed on all activities that were organized in any LPD. According to our daily monitoring of the Facebook, 225 awareness activities took place in a total of 169 schools. Facebook continues to be a powerful tool and most of the participants are very active posting and sharing information. SCPA has managed to build a strong team spirit and to foster communication, and exchange of experience among the youth educators and we intend to boost this activity during next reporting period.

The SCPA Program has continued logistic support to the awareness campaigns. The CPOs are provided with marketing materials distributed at the workshop and all 61 youth educators were equipped with an electronic version of the manual and supporting materials like PPT presentations, videos and awareness spots.

## Pillar III – Domestic Violence Support

Activity 3.1.e. - Setting up Referral Mechanism and Multidisciplinary Technical Team in TLPDs

Overall, progress has been made in the functioning of Referral Mechanisms established lately or revitalized, yet there is a long way to make them fully functional, effective and sustainable.

In September, a presentation on Referral Mechanisms to the new mayors and municipal councilors in Kukes and Gramsh following June elections were conducted. The aim was to raise awareness on the legal obligations of the Local Government Units on Referral Mechanisms establishment and functioning and taking the opportunity to lobby for more budgets and services related to domestic violence.

During September – November, four meetings of the Multidisciplinary Technical Team (two in each municipality of Gramsh and Belsh and one in Kukes) were organized, where local gender based / domestic violence cases were discussed and provision of necessary services and actions were coordinated.

The operational Multidisciplinary Technical Team in Kukes was partly subject to turnover of its members due to the local elections of June 2019. For that reason, in October a one day training was organized by the Albanian Institute for Social Innovation. The main topics of the training were the strengthening of the multi-disciplinary collaborative strategies among newly appointed specialists in local level in responding the violence against women, international norms and standards on DV, domestic laws and by-laws, factors underlying violence against women, preventive approaches, responding to violence against women: the role of the police, inter-agency collaboration and support.

In addition, through funds and projects of the Round III of the GS, the referral mechanism is newly established in Peqin and Librazhd municipality. The PMT supported with technical assistance the implementing team of “Tjeter Vizion” in Elbasan facilitating the process as per approved procedure. The constitutive meeting of the mechanism in Librazhd was held on 17 July, and the one in Peqin on 19 September.  Over the period September – December four training sessions with the Multidisciplinary Technical Team members were organized, aiming at the upgrade of their technical capacities.

On a general note, addressing domestic violence requires long-term commitments, human and financial resources, capacities and constant efforts to keep it on the agenda of local governments to further progress in preventing it.

Activity 3.1.f. - Support preparation & carry on awareness raising campaigns on DV cases

In support to the yearly 16 days of activism against violence against women, the SCPA Program joined the UN SG’s campaign UNiTE to End Violence against Women. In this framework, awareness activities were organized in 6 districts (Vlorë, Elbasan, Kukës, Korçë, Lezhë and Pogradec) attended by students of 26 high schools. 12 local NGOs implementer of Grant Scheme projects were engaged in the process of coordination and organization of the campaign activities.

The awareness campaign was designed in consultation and cooperation with the Ministry of Interior and the ASP, taking into account their specific needs and requests and it was coordinated and synchronized with the UNDP national campaign.

Promotional materials such as posters, leaflets, pens with logos, promotional badges, ribbons, etc. were designed, produced and distributed in the designated districts.

The final event of the DV campaign, which was prepared to be largely attended and that would be carried out at the space of the Gallery Pavilion REJA, was cancelled due to the extraordinary situation created by the November earthquake.

Activity 3.2.g. Develop a Capacity Development Plan related to domestic violence needs

The Capacity Development Plan related to domestic violence needs was drafted in November and shared with the ASP specialists. It is a structured approach to meet the capacity-building needs of the ASP, designed to help a systematic development of the police’s knowledge and skills required to respond in an effective and appropriate manner to violence against women. This includes measures to prevent violence against women, ways to respond to and investigate acts of violence, and resources to meet the needs of victims.

This capacity building plan consists of three essential pillars that correspond to critical tasks: establishing priorities of capacity-building needs, developing capacity-building programs, and a management strategy that will allow these capacity-building programs to be implemented within the context of the budget and resource constraints.

Activity 2.j. Specific training for CPOs and crime inspectors on DV cases

In coordination with the ASP HQ and the Academy of Security, the SCPA program will deliver the training for the two TLPDs of Kukes and Elbasan on the implementation of the latest changes and amendments regarding the preliminary immediate protection order and the conduct of risk assessment for domestic violence cases.

The first training session was organized on 17 December in LPD Kukes with the participation of 25 police officers of commissariats of Kukes and Has. The second training session was organized on 18 December in Bajram Curri with the participation of 17 police officers from Tropoja commissariat. The target group of both training sessions were the community policing officers and the crime specialists.

The aim of the training was to provide the police officers with sufficient skills to carry out structured risk assessments and contribute to the uniform implementation of the specific legal provisions introduced by the recent amendments in DV law. Risk assessment procedures are intended to assist professionals in analyzing concrete situations, introducing a greater objectivity, identifying the level of the present risk and thus guide police action better in order to increase the safety of victims.

The training for LPD Elbasan will be organized in the beginning of 2020.

Activity 3.2.k. – Restructuring and reorganizing internal premises in pilot commissariats

The Interview Unit for Minors and Victims of Domestic Violence in at Elbasan LPD underwent a complete reconstruction and refurnishing. In addition, the installation of state-of-the-art audio and video recording equipment was carried out. This is the first set of equipment of this type installed in Albania, enforcing the provisions of the Code for Criminal Justice for Children, allowing recording of the victim’s interview in the presence of defense lawyers and prosecutors. The defense lawyers and prosecutors may observe and follow the interview with the victim, carried out by trained police officers. They can communicate with the interviewer in real time and indirectly ask questions or clarifications to the victim. The entire interview will be recorded and can be used as trial evidence. A special software is installed to manage the information. The program spent 19.000 euro for the equipment and 5.500 euro for reconstruction and refurbishment of the premises.

A one-day training was conducted with the DV and crime investigation experts of Elbasan LPD for the use of the equipment. A user manual is prepared for this purpose.

By providing this unit with equipment and expertise, the most recent international interviewing standards and norms are met. This is intended to limit the number of interviews, statements and hearings involving minors and victims of violence as well as to enhance the quality of the investigation and evidence.

## Horizontal Activity - Grants Scheme

In accordance to the Work Plan the fourth call for applications was launched at end of December 2019 in three regions: Tirana, Kukes and Berat.

The terms of the call were formulated to support pillar I, II and III, meeting the objectives of the three components of the program and aiming at increased synergy of interventions and efficiency of use of SCPA resources. The focus areas of this call, as the ones of the previous calls, are:

- Empowering civil society organizations to support the establishment and capacity building of Local Councils of Public Safety and community-based coalitions with a view to improving relations and continuous cooperation between the Albanian State Police and local communities and building mutual trust.

- Improving the interaction between the State Police and other local actors, through initiatives to support establishing and consolidation the local referral mechanisms to enhance the quality of preventive measures and the services in cases of domestic violence and gender-based violence.

- Establishing and consolidating partnerships between the Albanian State Police and local communities with focus youth, through main subject issues such as conflict resolution, promotion of voluntarism, awareness on drug and substance abuse, road traffic safety, bullying and cyber-crime, human trafficking, homophobic crimes, etc. with an emphasis on prevention measures.

Locally based organizations were strongly encouraged to apply with the aim to maximize the use of local resources and capacities and fostering local ownership. The awareness campaign in this call for proposals consisted in broad information about the grant scheme and the fund opportunity offered to NGOs. The campaign involved a wide variety of media informing interested organizations and potential applicants about the Grant Scheme. This included newspaper advertisements, the internet, and social media/network to share the information as well direct notification by sending email messages to NGOs.

The deadline for application is the 23 January 2020. The selection process through the engagement of the Local Selection Committees that will be established in each region, is expected to end in February and the implementation of the projects to start in March 2020.

Meantime, the implementation of the projects of the round 3 continues. The focus of interventions of this round is the domestic violence and gender based violence. 8 projects out of 17 (47%) are based on activities that support DV awareness raising and consolidation the local referral mechanisms.

Some highlights from activities and outputs from these grants are:

- In the frame of the project “Community Policing and Disability–Partnering for Inclusion” implemented by the “Albanian Disability Rights Foundation” an assessment was conducted  about accessibility and inclusion of the community of disabled persons to the services provided by the state and police structures at local level in Korça. The assessment included the level of physical accessibility to facilities, access to information and communication (information provided in alternative formats such as braille, easy-to-read format, or provision of interpretation in the language of signs).  An action plan is developed with concrete interventions, including timelines and financial costs. The findings and the recommendations of the study and the action plan were shared in a joint round table with representatives of the disabled persons community, police officers, representatives of the municipality, State Social Services, Local Health Directorate, etc. to ensure access, services and partnership between the state police and the community of persons with disabilities as well as local stakeholders.

- In the frame of the project “Community Policing Challenges and Prospectives in Vlora Region” implemented by the local organization “Vlora Youth Center” a mini survey on community policing was conducted in Vlora district. The findings of the focus group with citizens and police officers were shared in a consultative meeting among local stakeholders in Vlore with participation of representatives of the municipality, State Social Services, Education Directorate, head of administrative units, Local Health Directorate and representatives of the Domestic Violence Referral Mechanism. In addition, the NGO supported the establishment of the Local Council of Public Safety in Selenice and will support the activities for the next semester of 2020.

- The organizations “H.A.N.A”, “Albanian Center for Population and Development” and the “Shelter for Abused Women and Girls”, are taking on interventions in Lezha district and its suburb and rural areas to enhance capacities of the police officers and other member institutions of the local Coordinated Mechanisms of Referral to better respond to domestic violence and to better assist the violence victims, including practical implementation of community policing. The capacity building activities are followed by awareness raising for local communities and schools, to help community members to recognize violence against women and speak out against it and support victims.

- The locally based organization A2B is implementing the project “Community Policing with the participation of youth, against Domestic Violence” in Elbasan, which aims at strengthening the cooperation model between the school community, police structures and local actors in preventing domestic violence and creating a safe community. The project consists of capacity building activities and networking among police officers, psycho-social staff in schools, teachers, student governments and social workers in administrative units. Several informative sessions and awareness participatory activities such as football matches, art competitions and role plays are conducted by the peer to peer youth group, facilitated by the community policing officers, employing a variety of interactive methodologies which aims to enhance participants’ learning through interesting and fun ways.

- EDS Foundation, in the framework of the project “Safe on Bike”, delivered 10 bikes and related accessories to the CPOs in Vlora. One of the objectives of this project is to increase the awareness on road traffic rules and promotion of bike use, as an eco-friendly and sustainable transportation way. The other is to extend knowledge of the border police on operational and emergency procedures in marine navigation.

As for the projects of the second round, 16 out of 17 projects have already completed the activities, while one will continue further.

# Budget expenses

The total invoiced amount up until end of January 2019 amounts to 19 649 470 SEK, which corresponds to 65% of the total contract budget of 30.000.000 SEK.

The budget spending seems to be proportionally low, but that mainly concerns the reimbursable part of the budget, which is “back loaded”, i.e. where payments comes late in the project. This concerns for instance the Grant Schemes, infrastructure investments and surveys where we foresee that the remaining funds will be spent in 2020.

As for the fee spending, this is well on track for the PMT, while for the part under assignment costs (mainly local and international short-term experts) also are back-loaded (mainly IT-experts for developing software).

We are asking Sida for budget reallocations shown in the Budget Annex, which find judge necessary to implement the suggested activities for 2020.

# Focus for the next phase

The project is entering its last year of implementation and activities are very intensive. In this phase the aim is to consolidate what was achieved so far and to support implementation in practice of the ideas and recommendations shared with the ASP and approved by them. It is important to ensure steady and continuous improvement .

Activities under the first pillar will be the most important, as usual. The focus for the next reporting period will be:

- Support the TWG and the LPD Elbasan with implementation of the pilot solutions for the police zone and the functions for CPOs. In close cooperation with the ASP TWG, the project will monitor the implementation of the recommendations in practice.

- Support the CPOs in Elbasan LPD with equipment (laptops) and refurbishment of premises in rural areas (desks, chairs and small reconstruction of premises, where needed).

- Support drafting amendments in regulations of the new SOP for the CPOs, as well as the implementation of the model for the police zone.

- Preparation of the staff of the LPD Elbasan for the changes (e. g. information campaign, training on the job, training of computer skills).

- Implementation of a daily (quality) report for actions/activities of CPO and development of progress reports.

- Support the ASP Department of Public Security regarding the organization of a volunteer Police Service.

- Finalize the training for CPOs (4 remaining groups of Tirana LPD).

- Finalize the software for management of requests and service provision in the Reception Halls, and supporting the digitalization of services at the same time.

- Support the set-up of the LCPS in Kukes municipality and support the activities of the LCPSs already established in the TLPDs

- Support the ASP and the MoI drafting the new Strategy of Public Order (part related to Community Policing).

- Continue the process of coaching in the two pilot LPDs in Elbasan and Kukes for the Sector of Analysis and Monitoring.

- Train the new members of the Sector for Strategic Analysis in some LPDs (compressed training based on the existing training program for analysts). Support and train the other staff in reporting against the annual strategies.

- Conduct a training and coaching process for drafting and development of strategies based on the guideline which was already compiled by the program. This training is relevant for both LPDs and ASP HQ strategic analysis sector staff.

- Launch the next National Police Satisfaction Survey.

- Deliver the training for ca 180 security officers and social workers in secondary schools with the aim to extend the three awareness campaigns in these schools during 2020.

- Support the CPO Educators work with laptops and projectors to be used in presentations in elementary  schools. Support with other logistic materials.

- Collaborate with the ASP and MoI in implementation of the activities in the frame of “2020 the year of traffic safety” campaign.

- Support the activities of Referral Mechanisms in the targeted municipalities.

- Deliver the training for Elbasan LPD on amendments to the law on domestic violence and implementation of risk assessment mechanism.

- Finalize the selection of winners for Round 4 of the Grant Scheme (regions of Berat, Kukes and Tirana).

- Monitor the implementation of the programs financed through the Grants Scheme and provide support to the CSOs.

Study visit?

One LSMS? We have enough funds for 2 if I recall, and then we need to do one during spring and a final one during fall, or?

# Annex I – Updated Logical Framework

|  | Intervention logic | Objectively verifiable indicators | Sources of information | Comments |
| --- | --- | --- | --- | --- |
| Overall objective | Contribute in building mutual trust and partnership between police and communities in order to create safer neighborhoods. | Safety situation in Albania positively assessed | - Ministry of Interior reports - ASP reports - Statistics - European Commission Progress Reports - Project reports | Based on PSS of May 2018 cc. 63% of Albanian citizens consider the ASP is doing a “good” or “very good” job. 75% of Albanian citizens declare they feel “safe” or “very safe” walking in their neighborhoods at night. Only 62% of citizens are willing to call the police when they see a crime committed on the streets. |
| Specific Objectives | - Accountable, capable and responsive institutions providing community safety & security - Citizens play an active and positive role towards their personal & CSS | - Albanian agencies skills to address community safety issues enhanced - Increased citizens personal engagement and through CSO in safety and security issues | - Ministry of Interior reports - ASP reports - Statistics - Program reports | 555 CPOs trained by the program 40 Analysts Workshop for 60 CPO-Youth Educators 9 workshops for the managing staff and analysts 10 LCPS activated or established. 45 CSOs contracted to support safety initiatives in local communities. |

| Mandatory outputs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Areas of Intervention | Objectively verifiable indicators | Sources of information | Outputs July-Dec 2019 | Overall outputs |
| Pillar 1 | - Support the ASP in enhancing the efficiency of CP structure - Strengthening local partnership - Capacity building | - Thorough analysis of the TLPDs conducted. - Identification of the elements best fitting to Albanian context done. - Revised job description/job profile of the CPOs - Revised SOP presented - ASP HRM assisted to assess current CPOs against new job profile - CPO work in two TLPDs is coached, monitored and assessed - Material support provided to the selected CPOs of the TLPDs - Virtual Police established in the TLPDs - RH business processes enhanced and material support provided to RH of the TLPDs - LCPSs in the two TLPDs revitalised and established. - The police representatives in the LCPSs coached and sensitised on the police role in the forum - Training curricula for all police officers on the CP principle developed and modernised. Staff trained - CPOs curricula revised and enhanced; ToT training - RH staff trained; ToT training - Study Visits carried out | - Programme reports - ASP reports - Surveys - Statistics - Meetings - Minutes of Meetings - No. of staff trained | The assessment report on CPO tasks and functions compiled and approved by JWG Prevention Room for Kukes LPD reconstructed and refurbished Reception Hall and detention premises of Tropoja reconstructed Prevention Room for Kukes LPD reconstructed and refurbished 230 CPOs trained in LPDs Dibra, Korca, Fier and TiranaThe LSPSs kick-off meeting in Peqin, Vlora and Selenica municipality The CPOs of Diber, Fier, Korce, third group of Durres and two groups of Tirana (approx. 211) trained by the program. | The TWG started working on the assessment report recommendations New CPO job description drafted Elements for CP fitting Albania case recommended. 15 job descriptions recommended for LPDs and Commissariat, including CPO position. 60 bikes and other firefighter equipment providedCommand and Control Room in Elbasan & Reception Hall and other premises in Has Commissariat and Librazh commissariat renovated. Command and Control Room of Kukes LPD co-financed with the local businesses. Prevention Room for Kukes LPD reconstructed and refurbished Reception Hall and detention premises of Tropoja reconstructed Web constable established in TLPDs. Draft ToR for RH software elaborated and re-engineering of services completed. LCPS in Elbasan is active, while LCPSs in Has, Tropoja, Librazhd, Perrenjas, Gramsh, Patos, Kavaja, Peqin, Selenica and Vlora established. Training curricula for CPOs drafted, ToT delivered and training provided to 555 officers. Coaching provided for Elbasan and Kukes LPDs. Study visit in Slovenia and Croatia focused on CP practice organized in June 2018 and study visit to Germany organized in May 2019. |

| Pillar 2 | - Strategic Planning and performance evaluation - Coordination between stakeholders - Communication | - Progress report and lessons learned on the Policy Document 2015-2017 conducted; New Policy Document 2018-2021 drafted - Capacities of the organization at all levels to effectively monitor and assess implementation of policy documents and action plans increased - An efficient monitoring system put in place - The two TLPDs supported to draft periodic progress reports and identification of bottlenecks - Capacities to externally monitor and evaluate the work of the police increased; national and local surveys conducted - LCPS used an efficient mechanism to address local issues - Partnerships with citizens and other local contributors increased - Integrated Communication Strategy of ASP implemented - National Awareness Campaigns of different topics carried out - LPD spokespersons trained and their job description/profile reviewed. - The PR/Communication curricula of the Academy of Security for initial and continuous training reviewed | - Documents, reports, interviews - Notes from TGPM - Assessment of Community Policing practice - Monitoring and Evaluation - Surveys - Statistics - ASP reports - Visibility materials | A workshop for all the LPD directors organized SOP for the new sector proposed by the program and approved by the ASP Workshops with analysts and managing staff of Shkoder, Korca, Vlora, Fier, Elbasan, Kukes, Diber and Lezha LPDs 0 CPOs- Youth Educators participated in a workshop on the new themes and experience sharing LSMS II for Elbasan and Kukes compiled and data to be shared in the upcoming period Monitoring of the Educators Online Forum and advising them | CP Document 2018-2020 approved. Monitoring plan drafted. Analysts and managers in 2 TLPDs trained (25 participants in 10 training days). Coaching delivered (20 coaching days). 16 analysts in other LPDs trained in 8 days modules. Police Satisfaction Survey 2018 completed and results shared with stakeholders. LSMS I & II for Elbasan and Kukes completed and results shared and discussed with stakeholders.Results of PSS presented in Elbasan LCPS and members invited to take measures. 12 LPDs spokespersons trained in 3 days training and coaching provided as follow up. Newsletter for Elbasan and Kukes LPD produced and web constable launched. Manual for the CPOs Educators prepared; 5 days training for 60 participants delivered. 3 awareness campaigns developed. Web Forum for Educators developed. Leaflets and booklets printed and distributed. Workshop with managing directors of the LPDs Workshops with analysts and managing staff of 8 LPDs. |
| --- | --- | --- | --- | --- | --- |

| Pillar 3 | - Strategic Level Interventions - Capacity Building and Strengthening - Infrastructure and Logistics support | - Report on Prevention Approach completed - Legal and by-legal framework on DV revised - SOPs on DV cases enhanced - Data collection system for the ASP, Prosecution Office and Courts established - Referral Mechanisms established and functional in TLPDs - Awareness campaigns in TLPDS against DV and gender based violence - Capacity Building Plan on DV elaborated - Training curricula and modules on GBV and DV upgraded - Refreshing training delivered in all LPDS on GBV and DV - Training for CPOs and CIDs delivered - The DV interviewing areas in the TLPDs commissariats restructured and reconstructed - Material support for the CPOs and CIDs in agreed commissariats provided. | - Project Reports and documentation; - UNDP, UN Women, OSCE reports ; - Ministry of Health reports; - MoJ and Prosecution Office Statistics. - Police reports/statistics; - Project Reports; - Assessment reports & Surveys; - Monitoring & Evaluation Plan; - UNDP & UN Women databases, maps and reports - The Ombudsman /Internal Control Service /M. of Health /M. Education and Sciences / Local Government reports | Consolidation of the DV Referral Mechanism in Belsh, Gramsh and Kukes through support Awareness raising campaign during 16 days of activism against violence against women in 6 districts Vlore, Elbasan, Kukes, Lezhe and Pogradec. Capacity development plan drafted 42 police officers of Kukes LPD trained on addressing DV cases and risk assessment. Interview Unit for minors and DV victims in LPD Elbasan created (works + equipment) and staff trained | Referral Mechanism established in Gramsh, Belsh and Kukes and continuous support provided. DV Awareness Campaign implemented in November-Dec. 2017, 2018 and 2019. Friendly interview room in Librazhd and Comm. 4 in Tirana completed. Interview room created in Has. The report on Prevention Approach finished and submitted Capacity development plan drafted 42 police officers of Kukes LPD trained on addressing DV cases and risk assessment. Interview Unit for minors and DV victims in LPD Elbasan created (works + equipment) and staff trained |
| --- | --- | --- | --- | --- | --- |
| Grants | Empower civil society organizations to embrace and implement the CP philosophy and support to combat DV. | - Grants Scheme implemented as planned and scheduled | Grantees reports Program Reports Surveys ASP reports | 16 out of 17 projects from Call 2 completed Fourth call launched | 45 grants’ contracts signed, covering 10 regions in Albania 403.744 Euro contracted. 27 contracts completed and 18 still in implementation (rounds 2 and 3) |

# Annex 2 Risk Matrix

|  | Risk Factor (security, political, operational , financial, reputational) | Impact | Likelihood | Mitigation Strategy and Responsibilities |
| --- | --- | --- | --- | --- |
|  | High-level buy in |  |  |  |
| 1 | Overburdened national partners / lack of resilience - Political unrest especially during the pre-election period - Excessive demands of national partners results in them losing interest or willingness to participate in program - Other demands results in low priority of community policing - National counterparts may not be able to operate at the speed desired of the PMT to design and set up specific activities within the program streams - Pressure by senior leadership to produce results within unreasonable timeframes (including pressure focusing on outputs, rather than outcomes) | Medium | High | - Pay attention to specific local deadlines or other demands - Use existing local systems and procedures (i.e. monitoring systems, rather than setting up parallel structures) - Sida/PMT to ensure that international community is communicating and cooperating with each other and ensure common interest and objectives in community policing - Capitalize on the demonstrated interest from senior MoI and ASP leadership in the program - PMT to ensure sensitization across senior MoI and ASP leadership of the program work plan and estimated timelines |
| 2 | Lack of, or unwillingness of, stakeholders to participate and cooperate - Resistance or mistrust from communities and local government / decentralized institutions to cooperate with police - Partners within the regions do not feel they are part of a process | Low | High | - Ensure transparent processes and encourage local partners to actively participate - Support for partnership approaches can be developed with the relevant line ministries (advocacy and liaison) - Risk management matrix and development of mitigating strategies is carried out collectively by the SC - Capitalize on the excellent partnerships developed during the first phase of the program |
| 3 | Major reshuffle of key police personnel - Key personnel are moved to other positions before progress can be institutionalized within the ASP or LPDs - Long term vacancies in key positions – The Chief of Sector for the CP Sector at the Headquarters is vacant since 8 months and staff is overburdened with tasks | Medium | High | - PMT to monitor personnel shifts and timely reporting to SC - Explicit approach by the SCPA to strengthen institutional capacity not just focus on individuals |
| 4 | Lessons and progress made as a result of the program are not recognized by decision-makers and do not inform future policy development - The SCPA seeks to develop institutionalized behavioral change. The gains of the program will not be sustainable if the changes remain solely at the individual level and do not influence policy changes that support cultural shifts in the way of working | High | High | - Sensitization activities on key lessons to be incorporated into the PMT program monitoring process - M&E program stream to include creating or developing mechanisms to ensure that the lessons are fed into MoI/ASP policy making bodies - The SMS Coordination stream will encourage cross-departmental cooperation and cohesion - PMT to be prepared to provide summaries of key lessons and changes to the MoI if/when a process to develop an MoI policy on safety and security commences |
| 5 | Program loses coherence - Pressure by the MoI/ASP to provide support to ad hoc activities outside the planned design - Program impact becomes diluted / program loses focus as a result of reacting to new/additional requests for individual activities from the MoI/ASP | Medium | Medium | - SC consent to be required, in addition to Sida’s, for any substantial deviations or requests for new assistance - Requests should be accompanied by clear analysis of how the new request contributes to achieving the program’s direct outcomes - PMT to ensure that requests for new activities are included in the preparatory documents for the SC |
|  | Program processes |  |  |  |
| 6 | Corruption or allegations of corruption in program (particularly relevant for the Grants Scheme) - Misuse of funds and poor accounting - Favoritism of particular groups for projects | High | Low | - The SCPA shall continue the excellent transparent practices for their GS - Emphasis on transparency throughout program - Clear and transparent selection procedure for all projects - Allegations of corruption to be followed up immediately by the PMT and the Embassy/ the SC informed |
| 7 | Experts are not of a sufficiently high quality - PMT staff members do not have the capacities to deliver the required quality of work - Short-term experts do not provide work of a sufficient quality / relevance to the Albanian context | High | Medium | - FCG / the Embassy / ASP / MoI quality control of program’s outputs - Use of the monitoring mechanism to track performance and follow up with feedback from the beneficiaries on expert performance - Clear terms of reference and expected deliverables to be developed for short-term experts etc. |
|  | Sustainability |  |  |  |
| 8 | ASP and MoI do not follow the recommendations regarding budget allocations and staff reshuffle after TLPDs piloting - Diversion of ASP funds to the TLPDs in order to ensure their short-term success - Diversion of ASP funds away from the TRPDs because they are covered by the program - ASP/ MoI do not systematically provide support to TLPDs | Medium | Medium | - Relative allocation of funding to ASP LPDs (including the TLPDs) to be monitored as part of the PMT monitoring mechanism - Concerns to be raised to the SC - Clear and transparent selection criteria for the TRPDs - Sensitization process across the ASP on the program – especially regarding progress being made, lessons learned, and dissemination and replication activities |
| 9 | Lack of responsiveness to adapt proposed models to Albanian specific situation - Models provided by PMT for Pillar I do not fit with specific conditions | Medium | Low | - PMT will not design a “model” for the community policing in Albania, but will provide different elements of a model - The elements will be illustrated by international examples and provided with their “pros” and “cons”, aiming to develop an Albanian model. |
| 10 | Shift in international engagement - International development programs fail to achieve stated aims and objectives in areas linked to the SCPA - Sida project overlaps or competes with other international project/demands and overburdens local partners | Medium | Medium | - Key international community (IC) actors have been informed/consulted throughout the design process - PMT to map out what key deliverables from other programs will influence their activities - Program proposal and future program activity documents to be shared widely with DDPFFA and the IC |
| 11 | Albanian authorities do not start to take on elements of budgetary responsibility - Whilst the SCPA will absorb the costs for monitoring activities in the early stages of the program (e.g. citizen perception surveys) these will need to be taken on by the MoI/ASP progressively as the program unfolds - Any budgetary impacts for new procedures for the LPDs will also need to be incorporated into MoI/ASP budget planning | Medium | High | - Exit strategy contains clear mechanisms for the GoA to adopt gradually increasing funding responsibilities throughout the program – framework to be developed during the inception phase and built up over years 1 and 2 - Constant monitoring |
| 12 | Transfer of procedures, skills and expertise to other LPDs is not done in a sustainable way - Pressure to replicate TLPD processes and approaches to other LPDs before they have been monitored, evaluated and proven - Lessons and new/updated ways of working are never transferred | Low | Medium | - Role of the IPA in advising on time lines - SC consensus on large scale replication activities - Continuous monitoring on progress and development of when aspects will be disseminated - Selection for LPDs based on international good practice - Individual risk analysis / mitigating strategies to be developed for specific dissemination/replication activities |

# Annex 3 - Participants/beneficiaries in SCPA activities

Increasing participation in program’s activities has always been considered by the SCPA as a useful tool in enhancing the effectiveness, efficiency and coverage of project benefits.  In the context of developing participation as an empowering process in which “experts, local and central bodies, in partnership with each other, identify problems and needs, mobilize resources, and assume responsibility to plan, manage, control and assess the individual and collective actions.

For that reason, program has adopted the approach of closely monitoring participation and number of beneficiaries in program’s; activities as a whole.

During this reporting period PMT achieved organizing in total 251 activities; 97 were regular meetings with the MOI, ASP HQ, LPDs, Local government and other stakeholder representatives. Among the most important ones were: 1 PSC meeting, 1 JWG meeting and 1 LCPS meetings in Peqin in the area of TLPD of Elbasan. PMT organized 11 rounds of trainings that involved 201 CPOs from LPDs of Tirana, Fier, Dibra, and Korca; a group of on-the job training for the staff of the newly created sector of Analysis, Reporting Monitoring and Evaluation of LPDs of Kukes, Diber, Shkodra, Lezha, Elbasan, Korca, Fier and Vlora preceded by a one-day workshop with 40 senior management staff of 12 LPDs. One training/workshop was delivered in the Academy of Security for 61 youth educators selected from 12 LPDs.

During this reporting period, PMT also organized 5 Technical Work group meetings for drafting the SOP and Job description of CPOs and revising the job description of patrol service in the framework of the monitoring report on CPO situation. Regarding the DV Pillar of the program, were organized 49 activities 4 activities aimed at either establishing or running existing DV referral mechanism committees in Elbasan, Peqin, Saranda and Pogradec. PMT has also been active in organizing DV training workshop in TLPD of Kukes involving 25 CPOs and CIDs of Has, Kukes and Tropja commissariats. Also in the frame of national campaign of 16 days of activism against gender based violence 45 activities were organized in 7 regions of Albania namely: Tirana, Durres, Elbasan, Kukes, Fier, Shkodra and Gjirokastra involving 31 schools in total.

Conveyed in figures, activities involved a total of 4205 persons out of which 572 were ASP personnel, 57 were senior ASP police officers, 44 midlevel police officers and 471 police officers who took active part in the activities. Grant scheme activities held a good-sized amount of weight in both activities and participants

PMT has been focused to emphasize the importance of a good gender balance in all three component areas. Gender indicators were assessed in all of the activities, meetings, workshops, seminars and trainings. Exclusively, the PMT guided the activities of the Grants Scheme towards the establishment of gender indicators, including an understanding of how contacts between the police and young citizens might differ (pending not only on gender but also on ethnicity and geographical extent).  Also, PMT noted a rather good gender balance especially for the LPDs of Tirana, Vlora, Durres, Elbasan, Kukes, Fier, Korca, and Lezha.

Over all, the PMT assessed that: 58% or 2850 out of 4880 direct community beneficiaries were girls and young women; 58.5 % of the members in the implementing/core working groups of projects were/are women; 37 % of 183 police officers that have benefited from the activities were women police officers. Whereas only in the grant scheme activities the following data are relevant to quantitative gender indicators:  23.6% or 36 out of 152 police officers that have benefited by the activities were women police officers.

Program’s visibility and outreach with the public

During this reporting period the PMT succeeded in increasing the visibility of each component area. PMT applied several ways and means to expose the program.  Some of the effective ways to increase the program’s visibility were the following:

- Meetings with community-based organizations and other stakeholders in the framework of LCPS, and Grant scheme activities. These meetings were considered as an important way to expose the program’s objectives and philosophy but also as a spring board for establishing networks in order to cultivate long-term relationships.

- Workshops and training sessions were used successfully as an already proven networking facility.

- The online forum of CPOs –youth educators was a proven efficient tool to engage not only the assigned CPOs for education and work with youth but also ASP HQ and Academy of Security experts in exchanging experience with each other but also creating a network of CPOs. Almost all the trainees have now joined the forum. They have been very active to display their activities (over 872 photos uploaded) and have maintained regular communication and exchange of experience and work plans.

- The program’s web page which is user-friendly and accessible and providing open, consistent and searchable information about all programs. The performance of the program’s web page has increased substantially. During the past six months the web page was visited by 21.123 viewers. The Program’s social network accounts in Facebook, Google LinkedIn, and Twitter have also been quite active. The web page has been very helpful, especially in relation to the GS.

- PMT has continued the appreciated practice of producing and distributing a short excerpt of activities, summarized in the Monthly Newsletter of the Program. The Newsletter is distributed to almost 155 receivers, including ASP counterparts, international partner organizations, NGOs and other Program’s stakeholders.

Please note the number of the activities is the same as in the Inception Report. In this progress report only the activities implemented in the reporting period are mentioned.

During this last workshop 31 new CPOs joined the youth educators group. In that way all 12 LPDs have now 1-3 CPOs as youth educators.